## Choose File > Make a Copy...
Team: | Syntax Error Scallywags |  | Names: | Kevin Haro, Dustin Bachman, Elias Leverett, Adrian Collier
Class: | CS-371 | <= 479 or 579
70 | Days into Project | v R ¦¦ P v | Today is | 2022-04-29 | Fri | INSTRUCTIONS IN CANVAS
47 | Total Days | R | Hours Est. | Hours Rem. | BDV |  | 28 | 26 | 25.2 | 24.4 | 23.2 | 22.4 | 21.6 | 20.4 | 19.6 | 18.8 | 17.6 | 16.8 | 16 | 14.8 | 14 | 13.2 | 12 | 11.2 | 10.4 | 9.2 | 8.4 | 7.6 | 6.4 | 5.6 | 4.8 | 3.6 | 2.8 | 2 | 0.8 | 0 | -0.8 | <= BDEst.
[7 empty] | 28 | 34 | 34 | 32 | 32 | 32 | 31 | 31 | 31 | 31 | 31 | 31 | 29 | 23 | 19 | 19 | 14 | 14 | 13 | 10 | 9 | 9 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
Rank | Full Name | Initials | 28 | 0 | 0.4 | <= (BDV is set to 1 until the sprint starts.) | 28 | 34 | 34 | 32 | 32 | 32 | 31 | 31 | 31 | 31 | 31 | 31 | 29 | 23 | 19 | 19 | 14 | 14 | 13 | 10 | 9 | 9 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | Rank | Est. | Remaining | Person | Est. | Remaining
1 | Kevin Haro | KH | 20 | 0 |  |  | 20 | 21 | 21 | 19 | 19 | 19 | 18 | 18 | 18 | 18 | 18 | 18 | 16 | 14 | 10 | 10 | 10 | 10 | 10 | 7 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 1 | 20 | 0 | KH | 3 | 0
2 | Dustin Bachman | DB | 1 | 0 |  |  | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | DB | 13 | 0
3 | Elias Leverett | EL | 6 | 0 |  |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 7 | 0 | EL | 7 | 0
4 | Adrian Collier | AC | 25 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | AC | 5 | 0
— |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Unranked | 0 | 0 |  | 0 | 0
[7 empty] | Sprint Start | [30 empty] | Remaining
| Days between Scrums | [5 empty] | 0 | 5 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2
| Product Backlog | [5 empty] | Fri | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Fri | Sun | Wed | Fri | Sun
Rank | Feature | Assigned | Hours Est. | Hours Rem. |  |  | 2022-02-18 | 2022-02-23 | 2022-02-25 | 2022-02-27 | 2022-03-02 | 2022-03-04 | 2022-03-06 | 2022-03-09 | 2022-03-11 | 2022-03-13 | 2022-03-16 | 2022-03-18 | 2022-03-20 | 2022-03-23 | 2022-03-25 | 2022-03-27 | 2022-03-30 | 2022-04-01 | 2022-04-03 | 2022-04-06 | 2022-04-08 | 2022-04-10 | 2022-04-13 | 2022-04-15 | 2022-04-17 | 2022-04-20 | 2022-04-22 | 2022-04-24 | 2022-04-27 | 2022-04-29 | 2022-05-01 | 2 Days
---Creating Webpage---
3 | Make Calendar Page | AC | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Create Basic HTML Landing Page | EL | 4 | 0 |  |  | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
1 | Add CSS to Landing Page | EL | 3 | 0 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Add CSS to Calendar Page | AC | 0 | 0 |  |  | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Learn about XML
---Core Mechanics---
1 | Add Javascript Functionality | DB | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
1 | Combine HTML & CSS webpage with javascript code functionality | DB | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
2 | Add/Remove workouts from calendar | AC | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Add Workout Timer | DB | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
2 | Add button back to LP | AC | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
--Database Implement--
1 | Make a database (broad) | KH | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Things above this line are counted (i.e. up to line 100)

## Classic Project
Game: | Enter Your Game Title |  | Names: | Enter Your Names
2662 | Days into Project | v R ¦¦ P v | Today is | 2022-04-29 | Fri | INSTRUCTIONS: http://bit.ly/494BurndownInstructions
20 | Total Days | P | Hours Est. | Hours Rem. | BDV | This Doc: http://bit.ly/494BurndownTemplate | 52 | 51.9955 | 51.9887 | 51.9842 | 51.9797 | 51.973 | 51.9684 | 51.9639 | 51.9572 | 51.9549 |  | <= BDEst.
[7 empty] | 52 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46
Rank | Full Name | Initials | 52 | 46 | 0.0022539 | <= (BDV is set to 1 until the sprint starts.) | 52 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 0 | 46 | Rank | Est. | Remaining | Person | Est. | Remaining
1 | Jeremy Gibson | JG | 19 | 17 |  |  | 19 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 0 | 17 | 1 | 26 | 20 | JG | 19 | 17
2 | Mitchell Bloch | MB | 17 | 13 |  |  | 17 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 13 | 2 | 10 | 10 | MB | 17 | 13
3 | Austin Yarger | AY | 16 | 16 |  |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 16 | 3 | 16 | 16 | AY | 16 | 16
— |  | P4 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | P4 | 0 | 0
|  | P5 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Unranked | 0 | 0 | P5 | 0 | 0
[7 empty] | Sprint Start | [7 empty] | Project Due!!! |  |  | Remaining
| Days between Scrums | [5 empty] | 0 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 1
| Product Backlog | [5 empty] | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Tue
Rank | Feature | Assigned | Hours Est. | Hours Rem. |  |  | 2015-01-14 | 2015-01-16 | 2015-01-19 | 2015-01-21 | 2015-01-23 | 2015-01-26 | 2015-01-28 | 2015-01-30 | 2015-02-02 | 2015-02-03 |  | -2642 Days
---R & D---
1 | Learn Unity Basics | MB | 4 | 0 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1 | Learn Unity Basics | JG | 4 | 3 |  |  | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3
1 | Play Mario Bros. for research | MB | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2
1 | Play Mario Bros. for research | JG | 2 | 1 |  |  | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1
---Core Mechanics---
1 | Run | JG | 1 | 1 | [13 empty] | 1 | bar: 2015-01-14 to 2015-02-03
1 | Jump | JG | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2
1 | Hit blocks | AY | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4
2 | Hit blocks with item | AY | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2
2 | Grow with Mushroom | JG | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2
1 | Hit / Shrink / Death | MB | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2
1 | Kill enemies | MB | 1 | 1 | [13 empty] | 1 | bar: 2015-01-14 to 2015-02-03
---Enemies---
1 | Goombas | JG | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3
2 | Koopa | AY | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2
| Koopa Paratroopas | MB
---PowerUps---
1 | Mushroom | JG | 1 | 1 | [13 empty] | 1 | bar: 2015-01-14 to 2015-02-03
3 | Fire Flower | AY | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8
2 | Star | JG | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2
| 1 up | JG
---Art---
2 | Import sprites | JG | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2
3 | Sprite animation | MB | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4
3 | Animation FSM | MB | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 4
Things above this line are counted (i.e. up to line 100)

## Classic Version with Percents
Game: | Enter Your Game Title |  | Names: | Enter Your Names
2662 | Days into Project | v R ¦¦ P v | Today is | 2022-04-29 | Fri | INSTRUCTIONS: http://bit.ly/494BurndownInstructions
20 | Total Days | P | Hours Est. | Hours Rem. | BDV |  | 58 | 57.9965 | 57.9912 | 57.9876 | 57.9841 | 57.9788 | 57.9753 | 57.9718 | 57.9665 | 57.9647 |  | <= BDEst.
[7 empty] | 58 | 53.3 | 53.3 | 53.3 | 53.3 | 53.3 | 53.3 | 53.3 | 53.3 | 53.3
Rank | Full Name | Initials | 58 | 53.3 | 0.0017656 | <= (BDV is set to 1 until the sprint starts.) | 58 | 53.3 | 53.3 | 53.3 | 53.3 | 53.3 | 53.3 | 53.3 | 53.3 | 53.3 | 0 | 53.3 | Rank | Est. | Remaining |  | Person | Est. | Remaining
1 | Jeremy Gibson | JG | 25 | 23.3 |  |  | 25 | 23.3 | 23.3 | 23.3 | 23.3 | 23.3 | 23.3 | 23.3 | 23.3 | 23.3 | 0 | 23.3 | 1 | 26 | 22.8 |  | JG | 25 | 23.3
2 | Mitchell Bloch | MB | 17 | 17 |  |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 0 | 17 | 2 | 10 | 10 |  | MB | 17 | 17
3 | Austin Yarger | AY | 16 | 13 |  |  | 16 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 13 | 3 | 22 | 20.5 |  | AY | 16 | 13
— |  | P4 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | P4 | 0 | 0
|  | P5 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Unranked | 0 | 0 |  | P5 | 0 | 0
[7 empty] | Sprint Start | [7 empty] | Project Due!!! |  |  | Remaining
| Days between Scrums | [5 empty] | 0 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 1
| Product Backlog | [5 empty] | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Tue |  | -2642 Days | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Tue
Rank | Feature | Assigned | Hours Est. | Hours Rem. |  |  | 2015-01-14 | 2015-01-16 | 2015-01-19 | 2015-01-21 | 2015-01-23 | 2015-01-26 | 2015-01-28 | 2015-01-30 | 2015-02-02 | 2015-02-03 |  |  | 2015-01-14 | 2015-01-16 | 2015-01-19 | 2015-01-21 | 2015-01-23 | 2015-01-26 | 2015-01-28 | 2015-01-30 | 2015-02-02 | 2015-02-03
| ---R & D--- | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Learn Unity Basics | MB | 4 | 4 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
1 | Learn Unity Basics | JG | 4 | 4 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
1 | Play Mario Bros. for research | MB | 2 | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
1 | Play Mario Bros. for research | JG | 2 | 1.8 |  |  | 100 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 |  | 1.8 | 2 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8
3 | Something else | JG | 6 | 4.5 |  |  | 100 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 |  | 4.5 | 6 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ---Core Mechanics--- | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Run | JG | 1 | 1 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1 | Jump | JG | 2 | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
1 | Hit blocks | AY | 4 | 1 |  |  | 100 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 |  | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | Hit blocks with item | AY | 2 | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
2 | Grow with Mushroom | JG | 2 | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
1 | Hit / Shrink / Death | MB | 2 | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
1 | Kill enemies | MB | 1 | 1 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ---Enemies--- | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Goombas | JG | 3 | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
2 | Koopa | AY | 2 | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Koopa Paratroopas | MB | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ---PowerUps--- | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Mushroom | JG | 1 | 1 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | Fire Flower | AY | 8 | 8 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
2 | Star | JG | 2 | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| 1 up | JG | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ---Art--- | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Import sprites | JG | 2 | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
3 | Sprite animation | MB | 4 | 4 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
3 | Animation FSM | MB | 4 | 4 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Things above this line are counted (i.e. up to line 100)